## EAP
Brighter Futures Efficiency Action Plan (EAP)
Jan - April 2022.
Capital Investment
| Action | Details | Target | Evidence
|  |  | Date | Collection
1 | Loft insulation (main loft) | insulation has added (additional 200mm) ontop of the 170mm existing with new raised flooring and air void to prevent cruhsing / damage to the insulation. Total 370mm insulation and 30mm void between insulation and new floor | 2021-12-01 | reciepts & photos
2 | Loft insulation (secondary loft) | new loft insulation installed | 2021-12-02 | reciepts & photos
3 | Draughtproof Hatch (sec. loft) | new draft proof and insulated hatch installed | 2021-12-03 | reciepts & photos
4 | Internal wall insulation (1st floor) | waiting on installation in Sept | 2022-03-01
5 | New windows for rear of building | old windows have been removed and new double glazed windows have been installed | 2021-12-05 | reciepts & photos
6 | Replace side bar door with | new draft proof door has been installed | 2021-12-06 | reciepts & photos
7 | Seal old extracts / Replace with HMRV | small HMRV has been installed in the main room and all old extractors removed and sealed | 2022-02-01 | reciepts & photos
8 | Switch remaining to suitable LED lights | all lighting has been swapede with LED lighting, most rooms are activated by PIR sensors | 2021-11-01 | reciepts & photos
9 | Induction Hobs to replace gas | old oven removed and replaced with A rated induction hob and oven | 2022-03-01
10 | Replace old inefficient fridges | All old fridges and freezers removed (x7) an replaced with 2 energy saving units and 1 new improved unit) | 2021-11-01 | reciepts & photos
11 | Solar PV Array with battery storage | solar panels, inverter and batteries have been installed - DNO have approved expansion to add an additonal 6kWh inverter in September, total will be 9.76Kwh alongside our current battery storage | 2022-02-01 | reciepts & photos
12 | Water collection butt | 2 x Water butts are in the yard linked to gutters to collect rain water - researching rain collection for toilets use at the moment), have also installed solar powered watering system into allotments that takes water from butts | 2021-11-01 | reciepts & photos
13 | Replace faucets with water-efficient aerating set | Purchased new faucets and aerators, all now fitted and set to lowest flow | 2021-12-13 | reciepts & photos
14 | ASHP, Ibost and 2 x Thermodynamic panels to heat all water | Waiting on install date for ASHP and solar iboost, TD panels to be installed after the ASPH install
People Investment
| Action | Details | Target | Evidence
|  |  | Date | Collection
| Arrange Training for staff | Energy efficiency training delivered with DWR Welsh Water and Groundworks | 2021-11-01 | report & photos
| Arrange Training for staff, volunteers & Members | Energy efficiency training done with men and womens shed groups | 2021-11-01 | report & photos
| Energy efficiency to be added to induction | update employee and volunteer upduction system to include key energy efficency items and procedures | 2021-11-01 | report & photos
| Energy efficiency to be added to Trustee Agendas | from Jan 2022 Energy efficiency updates goto Trustee meetings | 2022-01-01 | Minutes
| Energy use policy and procedures to be inplemeted | Include energy saving into staff policies and procedures | 2021-12-05 | report & photos
| New month energy useage update report to be developed | Building coordinator to include with monthly report (now added to monthly list) | 2022-01-01 | report & photos
| Walk to work and vehicle sharing initiative to be launched | Bicyle available to staff, van can be used to come to work where all 4 staff travel together | 2022-01-01 | report & photos
| Staff Bicycle programme to be launched | 50% towards purchase of push bike for staff, free use of bicyle maintianance and repair system in RMS workshop (offered bike scheme) service kit and Mchecks can be done in workshop now, also offered 50/50 costs to join gym | 2022-01-01 | report & photos
| Continue allotment development | Continue sustainable food development onsite and offsite (Guys currently working on new allotment) | nil | report & photos
| Green Dragon Award | Research our ability to complete the award critera (waiting on Steve to link with Groundwork) | Q2 2022 | Award
| Conwy & Denbighshire Service Board Green pledge | Denbighshire & Conwy Councils have awarded Platinum award, fully complete | Q1 2022 | Award
Additional notes for reader
| Replace gas boiler and air source heating system | quotes obtained for hybrid system and full elec system, waiting to hear back from match funder (est. May 22)
| External wall insulation to entire building | This would require planning permission so outline application submitted to DCC, not expecting a quick or simple process
| EV ChargePoint | This is not feasable because it would cross the public footpath onto a loading bay (no parking)

## Evidence
Evidence